## Sheet1
Code | Activity | Duration | Dependency
1 | Proposition of project idea and commencement of planning | 28/07/2023 - 31/07/2023 | None
2 | Begin background research on aspects of project | 31/07/2023 - 01/08/2023 | 1
3 | Complete MATLAB Onramp courses | 05/08/2023 - 14/08/2023 | 1
4 | Identification of project requirements | 31/07/2023 - 02/08/2023 | 1
5 | Analysis of project requirments | 02/08/2023 - 04/08/2023 | 4
6 | Development of specfications | 07/08/20223 - 10/08/2023 | 4, 5
7 | Subsystem Breakdown | 10/08/2023 - 11/08/2023 | 4, 5, 6
8 | Write up of inter- and intra-subsystem interactions | 14/08/2023 - 16/08/2023 | 7
9 | Define acceptance test procedures | 16/08/2023 - 18/08/2023 | 8
10 | Setup of simulation using MATLAB | 21/08/2023 - 29/08/2023 | 3, 6, 8
11 | Testing of MATLAB simulation | 30/08/2023 - 01/09/2023 | 10
12 | Setup of physical system | 11/09/2023 - 12/09/2023 | 11
13 | Pi synchronisation setup | 13/09/2023 - 18/09/2023 | 12
14 | Development of code for signal acquisition and preprocessing | 13/09/2023 - 22/09/2023 | 11
15 | Development of code for time delay estimation | 13/09/2023 - 22/09/2023 | 11
16 | Development of code for triangulation/localisation algorithm | 13/09/2023 - 22/09/2023 | 11
17 | Development of user interface | 13/09/2023 - 22/09/2023 | 3
18 | Testing and debugging of Pi synchronzation | 14/09/2023- 18/09/2023 | 13
19 | Testing and debugging of signal acquisition and preprocessing | 22/09/2023 - 31/09/2023 | 14
20 | Testing and debugging of time delay estimation | 22/09/2023 - 31/09/2024 | 15
21 | Testing and debugging of triangulation/localisation algorithm | 22/09/2023 - 31/09/2025 | 16
22 | Testing and debugging of user interface | 22/09/2023 - 29/09/2023 | 17
23 | Overall performance evaluation | 31/09/2023 - 02/10/2023 | 13, 14, 15, 16, 17
24 | Final Testing | 02/10/2023 - 04/09/2023 | 23
25 | Final Report Write-up | 04/09/2023 - 18/09/2023 | 24